An illustrative design for a medium sized evaluation study

### AN ACCOUNTABILITY MODEL OF SCHOOL SELF-EVALUATION

Developed for use in the Indianapolis Public Schools

as the Learning Communities Analysis Project,

an effort of individual elementary schools

to gain greater recognition of their distinctive quality

Robert E. Stake, University of Illinois

# Summary

The Learning Communities Analysis Project.   This is a project to develop and initiate a procedure for indicating the quality of teaching and learning at a single school.  The primary audience is parents, community members, district administrators, and professional educators who have an interest in this particular school.  The people who have the greatest interest and acquaintance, the students, teachers, principal, and those parents who assist in its operation already know more about the quality of education here than will be found in the evaluation report.   In fact, they are the primary sources of data about school quality here.  It in large part is a self-evaluation--with assistance. and verification from the outside.  This evaluation should result in a report that will indicate how accountable the second group of people is to all those who support the school.

Rationale.  This is an evaluation procedure, to result in a presentation of the merit and shortcoming of the individual school.   As a self-study procedure, the activities will primarily be those of the school's own people, but with some help from others.   It will feature ratings of student achievement, programmatic teaching, and a foundation of support for instruction.  Although broad in scope, is not intended to describe the program in full detail, but rather to obtain a disciplined rating of quality of a few key characteristics of school quality.

Testing.  This report will be much more comprehensive than an indication of school quality based solely on standardized student achievement testing.   Test scores will be considered one indicator of achievement.  Such scores have an advantage in that the same questions are asked students at many schools, so that the students can be compared on learning represented by those questions.   But research and teacher experience provides extensive evidence that the quality of instructional programs and other services a school provides is far from adequately represented by test scores alone.   This self-evaluation procedure will provide a comprehensive summary of the quality of student learning, the quality of teacher instruction, and the quality of support behind the instructional program at the single school.

Self-Study.   This is not a procedure primarily to assist the professional staff of the school in reviewing and upgrading their work.  There are better procedures for that--some of which are shown below.  The best self-study procedures take much more effort and pinpoint strengths and weaknesses with much greater focus.  The staff may benefit some from participating in and ultimately reading the report of this LCAP evaluation effort, and this may assist in the district's move toward increasing school-based decision making, but it is primarily an accountability procedure rather than a management quality-control procedure.  This LCAP evaluation is to tell others how good the school is.

Promotional activities.  This evaluation and the resulting report is not intended to be a promotional device, something that tells the good side of the school without acknowledging the problems.   This procedure will depend on people who for the most part would like the school to be seen in its best light.  Many are proud of their schools.  Some are ashamed of their schools and hesitate to do anything that will further handicap them.  There will be certain checks and balances but the validity of the summaries of quality will depend on the success we may have in keeping people honest about what they see and value and are troubled by at this school.   The procedure includes indicators of the sincerity of the ratings.

Comparison of schools.   The most important aim of this procedure is to represent the best work accomplished and the troubles a school has encountered.   The schools of Indianapolis are different.   They serve different communities, they face different problems, they are peopled by unique people, they go far beyond the district frameworks in deciding what will be taught and how it will be taught.  With the SELECT SCHOOLS program, the schools are working hard not to duplicate each other.   The uniqueness of the schools will be apparent in the evaluation reports and direct comparison will be hazardous.   Still, the ratings and commentaries will be grouped under common headings of teaching, learning, and support.  Discussion of relative quality of schools will continue and  should be more enlightened, less simplistic, than discussions based  solely on standardized test scores.

School Report Cards.  There is an effort in Indiana to follow the lead of some other states in requiring each school to prepare a standardized school report card.  To date, these efforts have resulted in providing the community with information on certain gross characteristics such as budget, student enumerations, and test results.  Most of these report cards almost deny the school's unique efforts to provide youngsters with a sound educational and social support system.   The procedure offered here should be a better basis for verifying the accountability of the school to its program and to its community.

Burden.   Although this is a self-evaluation procedure, the work at each school will be largely done by a temporary research person associated with a university and the district office.   Each teacher and parent will be asked to make a brief contribution.  Some of them and the principal may choose to do more than that to assure that the program and the obstacles to success are fully presented.

Authority.   The expertise of assessing quality at each school will be that of the people most intimately acquainted with that school.   Expertise from evaluation specialists will assist with the operation procedures and respected outsiders will contribute to assurance that the effort to indicate quality is a sincere and comprehensible effort but the essence of understanding of quality will come from people who know the teaching, learning, and support for that school best.

## Program Characteristics

No one is well served by the present emphasis on standardized student achievement testing as the sole indicator of school quality.   The quality of instructional programs and other services a school provides is far from fully represented by test scores.  Educators, community leaders, parents and others need more comprehensive and accurate indicators of the strengths and weaknesses of each individual school.

The following are characteristics of my plan for developing a school self-evaluation procedure for use in the Indianapolis Public Schools:

1.  The plan would be a framework for individual school evaluation procedures which would culminate in a periodic School Evaluation Report.   It is conceivable that, in future years, the School District will require every school to prepare such a report annually.

2.  The first audience of the Report is seen to be those who care most about that school, but the public and District personnel will be important audiences too.

3.  The primary focus for school evaluation here will be the program.  Portrayal of instruction and student experience will be designed so that readers may judge quality for themselves.  Such portrayals will be supplemented with indicators of quality as seen by key individuals or groups.

4.  The evaluation effort will be designed

a.   to recognize poor quality as well as good quality,

b.   to facilitate improvement as well as to preserve endangered assets, and

c.   to leave individuals and schools with no greater difficulty in carrying out their responsibilities.

5.  The Report will feature indications of quality of both the achievement of the students and the provisions of the school for student learning, the latter including both teaching and administration.

6.  The evaluation of achievement will encourage authentic assessment (usually defined to parallel authentic teaching, with both aimed to develop student responsibility for organizing study, integrating subject matters, problem solving, and personal interpretation of learnings), especially in the use of portfolios, performance assessment, mentoring, and oral presentations.

7.  Indicators of student achievement will include standardized achievement scores but schools will have opportunity to emphasize whatever indicators best reflect student accomplishment in their programs.

8.  The uniqueness of each school's special programs and as well as teaching of the common syllabus will be afforded focus.  Particular examples of teaching may be used to illustrate quality.

9.  In addition to academics, provision will be made for schools to indicate what is being done to orient children to

a.  opportunities for of informal learning outside the school,

b.  work, careers, and the economic system,

c.  cooperative group activity,

d.  aesthetics, and

e.  principles and applications of ethics and morality.

10.   Authentication of quality schooling should not rest upon school personnel and students alone but should be substantiated by parents, specially trained volunteers, business and community leaders, and evaluation specialists.

11.  A large part of the competence of professional people is manifest in how they cope with problems.  This report form will acknowledge problems the school faces and illustrate the quality of the coping.

12.  The plan will draw attention to the importance of leadership by the principal and by teachers as well.  Involvement in the procedures should give staff members opportunity to improve their leadership skills.  Staff development training is anticipated.   The roles of central administrative personnel will be indicated.

13.   The Report will acknowledge that quality of schooling is influenced by support of administrative and resource offices, parents and parent organizations, and the community at large.  The presumption will not be made that all schools are supported equally.

14.   For the staff of the individual school, care will be taken to keep the burden of the procedure (including preparation of the report) at a minimum.  It is presumed that this evaluative activity will draw heavily upon existing formal and informal assessment and will contribute to staff reflection of its work.

15.   Where additional resources are needed to provide valid and credible indicators of quality, they shall be provided by the District.   If the District cannot provide them, the school should so indicate in the report.

16.   The plan will be compatible with previous work by IPS Strategic Planning Action Teams and Implementation Teams and will be informed by school reform efforts of the  state, regional accreditation, and national movements.

17.   The framework will emphasize program evaluation, not program promotion.

- The procedures and reporting will be designed in collaboration with evaluation teams from each school and will be designed to contribute further to the improvement of  school-based decision making.  Development of the procedures and tryout in 1993-94 should involve about six elementary schools in the District.

# Purpose

The purpose of the project is to:

1.  Build upon the work done by the IPS Strategic Planning Action Teams and Implementation Teams, work done at individual participating schools, and national efforts to focus evaluation on authentic measures.

2.   Improve leadership skills of IPS administrators and teachers.

3.  Begin a collaboration to identify grounds for the evaluation of all elementary schools.

4.   Give prominent attention to representation of the unique features of each school

5.   Continue to include parents and business and community leaders in all phases of this project.

6.  Invite school-level staff members, parents, business and community leaders and other key people to participate in learning about current evaluation methods.

(Explanation:  The term standards  indicates that the dominant evaluation of schools should be made with reference to common-for-all-schools, externally-determined definitions of performance:  minimum, excellent, and appropriate.  Schools serve different populations with different social expectations, with professional staffs of different preparation and competence, and with unequal resources.   Although it is essential to consider standards widely held within the community, the parent groups, the profession and the local staff--the primary standards to be used for the evaluation of individual schools are customized standards that reflect the common and unique mission of each independent school.  Many of the standards will be implicit.  The term grounds expresses the references on which evaluation should be conducted better than the term standards,.)

Rationale

The evaluator will sketch out a plan for consideration by the principals who expect to participate in a tryout.  With the assistance of the District Research Division, we will revise this sketch and agree on a plan.  When our plan has the support of District and community, we will devise a training schedule for preparing persons to implement the procedure.  That plan will be developed collectively and training will begin this summer

The rationale for the plan, subject to negotiation, is as follows:

1.  Education is complex.  The quality of school programs and student learning cannot be captured with a single indicator.  The prominence of achievement test means as an indicator of school success is presently so great that aspects of the quality of professional work and of student experience are insufficiently recognized.  This plan needs to substitute multiple indicators of school quality for the single indicator.

2.  It would be easy to identify ten or fifty potentially useful descriptive indicators but public and professional concerns about school quality, both for critics and defenders, are emotional and push us toward some degree of oversimplification.   Our best move appears to be to settle on about three indicators.

3.  The first indicator is of the ultimate concern of all:  student achievement.  That indicator needs to represent not only performance on universal ability goals as represented by standardized tests, but performance in specific courses including those special programs offered by the individual school.   Education is not only a matter of performance but of having a broad range of experience, including challenging opportunities to mature.  Maturation and experience are educational outcomes too.  All these can be aggregated to provide a single indicator of student achievement at the school.

4.  The second indicator should be something that tells of provision of opportunity for the student to learn, i.e., the quality of instruction and resources for study.  The most important factor here is the teacher, so we may call the second indicator: quality of teaching.  Or we might call it quality of the instructional program.  Teaching of course is not just imparting knowledge and giving assignments, but of monitoring a school situation that is conducive to learning and stimulates the youngsters to learn in and out of school.   It also includes deliberated selection of books, interactive activities, peer learners for collaborative learning, special programs, field trips.  It includes providing good evaluation of work, encouragement, guidance, mentoring, and human companionship.  These are some of the obligations of a school summarized by the notion of quality of teaching.

5.  Students and teachers cannot do the job alone.  There must be materials, space, transportation, meals, aesthetics, opportunities for healthy competition and more.  Providing these is the responsibility of parents, taxpayers, school administrators, District and State officials and support staffs.   Indication of the quality of education generated at a school cannot be understood without knowledge of the support that school is getting.  The third indicator of our evaluation procedure probably should be the notion of quality of external support.

6.  It is presumed that the report would be an annual report and that the procedure leading to it would take place once a year.

7.  Each of these three indicators can be backed up by subordinate indicators and with any amount and type of supportive illustration.   Just how the three indicators would be presented in a Report by the school can be varied in style and elaboration.   Whatever the presentation format, the minimum would be the three indicators.

8.  The most common scale for school matters is the grading scale running from A to F.   Or A+ through 13 levels ending at F.   This is just about the right amount of precision for our indicators and is familiar to most people.  It has been used successfully for many years by Gallup polling of public assessment of the schools and could serve our procedure well.   For each school, a summary three grades would be assigned, for achievement, teaching, and support.

9.  One of the good things about grades is that they convey the notion of the exercise of human judgment in indicating quality.  That is what we will have to have here.  There are no instruments or formulated procedures that will allow us to gather some objective data and with research validated weighting, arrive at scores of quality.  Our procedures will be deliberative and subjective judging, what we get from referees, Supreme Court judges, doctors, CEO's, yes, but also parents and teachers who make many important life decisions that way.  Reasoned, data-based, reflective, argued decisions.

10.  Evaluation is labor intensive.  We have the resources for building neither a technical nor observational system.   Whatever we do will strain our resources.  The only practical method may be for a few people on panels to review a digestible amount of information to arrive at grades within a relatively short period of review.  Perhaps there should be a panel of 3 or 4 people for each of the three indicators.   For achievement, how about a teacher, a parent, a community member, and an elder student.   For teaching, a teacher from another school, a parent, a district researcher, and a community member.  For support, a teacher, a parent, and a community member.   Since there is a strong interest in the business community in this effort, it could be that they should provide the community members.

11.  The review process for each panel will be to examine information presented to them, to discuss it, and to assign grades.   In each case some of the information will include data, e.g., ratings, grades, scores, exhibits, provided by the school staff, students or research office.   They may arrange for brief oral statements from volunteers or request contributions from the principal or others.   The work obligation for panel members is intended to be half a day.

12.  Each faculty member would be asked to provide some description and judgment of the school's student achievement, teaching quality, and quality of support, a confidential description.   Questions would be raised about problems, problem solving efforts, and success at that school in coping with problems.  Each teacher would be asked to consider what he or she might usefully present to the panel personally or anonymously to assist in gaining understanding of school quality.   The minimum burden per teacher would be perhaps half an hour.

13.  Persons in charge of special programs would be urged to provide the panel with brief descriptive summaries of process and accomplishment, using illustrative materials.

14.  Parents also would be asked to respond to similar questions in written form and would be alerted to opportunity to make an oral statement.

15.  It is presumed that the report would be an annual report and that the procedure leading to it would take place once a year.

16.  A single fourth panel would serve all schools as an authentication panel.  The panel would have substantial information about all schools.  This panel would review a draft copy of each School Report, plus information on how the school panels carried out their work.  It would add an authenticating statement for public circulation or would return the draft to the School Panels indicating reasons for withholding authentication.  The School could either issue the report without authentication, present grounds to the external panel for reconsideration, or redraft the report.

17.  It is the panel's responsibility to keep the evaluation attentive to both positive and negative information, to produce honest indicators of quality, not promotional statements.   This will not be easy, especially in grading the teaching.

18.  It would be the responsibility of the principal to see that the whole procedure gets underway and is making progress, but the principal would not instruct or supervise the work of the panel.   The principal probably will arrange to have the most positive information presented.   If the principal is dissatisfied with the work of the panel, he or she may add a brief attachment to the school report indicating in what ways the review was faulty and possibly to be disregarded.

19.  The burden for District evaluation personnel would be substantial, particularly in providing materials for rating and review of achievement, teaching and support to each of the panels.

- Much depends on the training of the panelists and others.

Strategic Planning Points

1.  Data on the quality of a program can be drawn

a.   from those already acquainted with that quality or

b.   generated objectively by instrumentation.

In either case, further interpretation is necessary.

2.  Present instrumentation (testing) is not adequately indicating the quality of teaching or learning in special programs.  To replace almost sole emphasis on standardized achievement test means, additional indicators are needed.  To be attended to, unfortunately, the indicators need to be few and simple.

3.  The cost of developing valid authentic assessment instruments or protocols and the cost of employing trained evaluators is prohibitive.   The best reports on special programs can be honest description of what is happening.

4.  School personnel already know much about what is good and bad.  (And they are pretty much the only staffing we can afford.)  When backed by technical training, their assessments can be expected to be reliable and valid.

5.  But if the assessing is done by the school's own people, they will sometimes be seen as self-serving.  The credibility of their assessments will be low.

6.  Credibility is increased by rigorous procedures, agreed-upon language, and the use of trustworthy reviewers.  Adding outsiders to assessment panels can increase the credibility.

7.  Working from information and ratings provided by school district people the panelists can generate a small number of indicators summarizing the quality of the program.

- Their indicators can be presented in an annual evaluation newsletter or report.  Complexity, contextuality, innovativeness, and the human character of the programs need to be portrayed in close proximity to the indicators.

Responsibilities of the consultant

1.  To conduct site visits and individual consultations with teams from each of the six schools, central office administrators, research department staff members, and others as necessary.

2.  To develop grounds and procedures for evaluating elementary schools.  Close attention will be given to recommendations of Blueprint 2005, the National Educational Goals, standards developed b y the Hudson Institute as part of its Modern Red Schoolhouse Project, the IPS Curriculum Framework, and other sources deemed appropriate by the evaluation teams.

3.  To assist in activation and operation of the comprehensive evaluation plan in each of the six schools including

a.  clarification of the role of norm referenced student achievement testing in the evaluation of schools

b.  identification of evaluation methods already in use which may be considered part of the  comprehensive plan

c.   inquiry into the state to which the school is achieving its goals

d.   alternative methods for evaluating individual programs.

e.  roles and responsibilities of

1.  the Research, Evaluation and Testing Department staff

2.   School Staff (Principal, Assistant Principal, Teachers , Parents

3.  Central Office Administrators.

f.  methods for measuring student and school progress

g.  format for evaluation reports which may be used consistently across all participating schools

4.  Train a core group of people from participant schools as well as the Research, Evaluation and Testing Departments staff and selected central office administrators in how best to implement the evaluation plan,  addressing as a minimum:

a.  data collection methodology

b.  data analysis

c.  interpretation and presentation of findings

d.  use of information to improve programs

5.  Join other resource people in assisting participating schools in the evaluation of their programs.

6.  Provide a model two-tiered comprehensive evaluation plan which

a.   evaluates individual schools according to local as well as district standards

- captures the experiences and accomplishments of students who are taught through different types of programs, strategies, and/or approaches

#### Questionnaire for the Principal

Principal:					School:

1.  What are the most important things to know about this school?

2.  Who are the people who most need to know more about this school?

3.   Do you have an idea of what the report ought to look like?  (Examples on display)

a.  the Classroom Report

b.  DuSable H.S. Report

c.  Central Park East Report

d.  A Corporate Annual Report

How long?

How chatty?

How honest about problems?

How comparative?

Should the report mention the sponsor of the evaluation?

How do you feel about the idea of evaluation panels?

Are you comfortable with having a graduate student dig into the files,  interview parents, kids, teachers,

and draft the report?

Is there any advice you can give me?

TEACHERS' RATING FORM				_____________________________

The Learning Communities Analysis Project						name

--an effort of the Indianapolis Public Schools

to help this school evaluate itself.

3.1

Dear Teacher,

This is to add your views to other information about the quality of education provided by this school.  Together it will make up a School Evaluation Report for the year.  We will treat your response anonymously.  Any remarks you make in the margins will be given serious attention, so please feel free to comment.

What Students are Learning

It is not expected that all of you will know a high proportion of the students at this school and not know very much about some you know, but please answer the following questions on the basis of what you do know about the students at this school.

Ratings of Quality of Experience for Students at this School

On the whole, what is the quality of experience for students at this school?

____Excellent     ____Very Good     ____Good     ____Fair     ____Poor     ____Terrible	(1)

How is this experience useful?  What is the quality of personal experience in-school which these students later can use to...

Regularly     	Sometimes high, 	Regularly

high quality 	  sometimes low   	poor quality

...direct their own learning.    .    .	_____    .    .    .    .	_____    .    .    .    .	_____	(2)

...prepare for employment.     .    .	_____    .    .    .    .	_____    .    .    .    .	_____	(3)

...participate in teamwork.      .    .	_____    .    .    .    .	_____    .    .    .    .	_____	(4)

...enjoy art and aesthetics.      .    .	_____    .    .    .    .	_____    .    .    .    .	_____	(5)

...solve ethical problems.       .    .	_____    .    .    .    .	_____    .    .    .    .	_____	(6)

What is the quality of academic learning by students at this school?

____Excellent     ____Very Good     ____Good     ____Fair     ____Poor     ____Terrible	(7)

Ratings of Individual Responsibility being learned by these Students

| 8. Considering the students at this school, their age, and the |  | ____All of them |
| --- | --- | --- |
| situations they face, what proportion of the students behave |  | ____Almost all of them |
| in a mature and responsible fashion? |  | ____Most of them |
|  |  | ____Maybe half of them |
|  |  | ____Only a few |
|  |  | ____None of them |

| 9. How much of a problem is there with students at this school acting aggressively against the school and their teachers? |  | 10. How much of a problem is there with students at this school acting aggressively against their fellow students? |
| --- | --- | --- |
| ____It is a major problem. ____It is a major problem involving only a very few students. ____It is a minor problem. ____It is no problem at all. |  | ____It is a major problem. ____It is a major problem involving only a very few students. ____It is a minor problem. ____It is no problem at all. |

11.  Considering their ages, how seriously do most students at this school take the responsibility of being good learners?

____Not seriously at all.      ____Most take it seriously.      ____Most take it too seriously for their own good.

| 12. How strong is the initiative among students at this school to protest against what they see as wrong and hurtful? |  | 13. ...and when they do protest, do they choose appropriate ways of expression? |
| --- | --- | --- |
| ____Very strong. ____Occasionally strong but more often not strong. ____Seldom strong. |  | ____Usually. ____Sometimes yes, sometimes no. ____Seldom. |

Ratings of the Quality of Teaching at this School

It is very important that you help us understand your views about the quality of teaching at this school.  Since it may be different for different subjects being taught, please answer each of the following as best you can.

Frameworks Teaching

From all the teachers and students you have known in the last two years at this school, what is the quality of teaching of...

Regularly     	Sometimes high, 	Regularly

high quality 	 sometimes low   	poor quality

...language arts and reading.    .	_____    .    .    .  	_____    .    .    .  	_____			(14)

...math.    .    .    .    .    .    .    .	_____    .    .    .  	_____    .    .    .  	_____			(15)

...science.      .    .    .    .    .    .	_____    .    .    .  	_____    .    .    .  	_____			(16)

...social studies.  .    .    .    .    .	_____    .    .    .  	_____    .    .    .  	_____			(17)

...art, music, aesthetics.      .    .	_____    .    .    .  	_____    .    .    .  	_____			(18)

...group activities of all kinds   .	_____    .    .    .  	_____    .    .    .  	_____			(19)

...work habits.    .    .    .    .    .	_____    .    .    .  	_____    .    .    .  	_____			(20)

Teacher Roles

We expect teachers to do many things for our children.  For each of the five roles below,  please indicate how good a job the teachers do at this school.

The teachers here          The teachers here

do a Good Job              do a Poor Job

Teachers need to arrange learning situations for children,

minimizing interference, recognizing when things are

right and wrong in the classroom.  .......................		______		______	      (26)

From their own knowledge, from books, and other sources,

teachers need to make information available to their pupils.  	______		______	      (27)

Teachers need to work well with the principal, other

teachers, and the rest of the school staff.  ..............		______		______	      (28)

Children are different.  Teachers need to pay close

attention to what each individual pupil needs.  ........		______		______	      (29)

Some things children need to learn are not very interesting.

Teachers need to find ways to motivate children.  ......		______		______	      (30)

Special Programs at this School

These are special programs at this school.  To the extent you are acquainted with them, how good are they?

Regularly     	     Sometimes high, 	       Regularly

high quality 	      sometimes low   	      poor quality

[Special Program #1]	_____	_____	_____		      (31)

[Special Program #2]	_____	_____	_____		      (32)

[Special Program #3]	_____	_____	_____		      (33)

[Special Program #4]	_____	_____	_____		      (34)

The remaining items have to do with the quality of support for classroom instruction coming from the principal's office, from the district office, from the community and the state.

School Leadership

In your view, what has been the quality of leadership

provided by the Principal of this school over the last year?

_____Excellent        _____Good        _____Fair        _____Poor        _____Terrible			      (35)

The Principal cannot provide all the leadership needed.  Teachers and other members of the

staff need to be leaders too.  Have the teachers and staff provided their share of leadership?

_____Regular leadership        _____Only occasional leadership         _____None at all			      (36)

Parental Support

37.  Teaching and learning are better if parents send their children to school with encouragement to learn.  Do parents of children at this school send the kids to school ready to learn?

_____Most do.	_____Some do, some don't.		_____Most do not.

38.  Parents support schools by paying attention to what teachers are teaching and to special schoolwide programs.  Do the parents here know what this school is doing?

_____Most do.	_____Some do, some don't.		_____Most do not.

39.  Some parents are able to volunteer help for teaching, for supervising, for program arrangements?  To the best they are able, do the parents at this school volunteer their help?

_____Most do.	_____Some do, some don't.		_____Most do not.

40  Some parents are good promoters for their school.  Others "bad mouth" their school, sometimes for good reason.  Are the parents of the children at this school good promoters?

_____Most are.	_____Some are, some aren't.	_____Most are not.

Strategic Plan

In 1992, the citizens of Indianapolis developed a strategic plan based on a collective vision of community responsibility for education.  Please indicate below how that plan supports the teaching and learning at this school.

| 41. Did the IPS Strategic Plan accurately identify crucial educational problems facing the community's schools? | _____Yes, it did. | ___No, it did not. | ___I have no knowledge about it. |
| --- | --- | --- | --- |
| 42. Is the IPS Strategic Plan a valuable guideline for school improvement at this school? | _____Yes, it is. | ____No, it is not | ___I have no knowledge about it. |
| 43. At this school, is it difficult to get outside support even for problems identified in the Strategic Plan? | _____Yes, it is. | ____No, it is not. | ___I have no knowledge about it. |

School System Support

This school depends on the school district, the community, and the state for financial support, direction, and encouragement.  How good a job are they doing?

Does Good Job      Does Poor Job

Does the Indianapolis Public School District

support this school right?	______	______	(44)

Does the City of Indianapolis

support this school the way it should?	______	______	(45)

Does the State of Indiana

support this school the way it should?	______	______	(46)

The Wisconsin Standards

Quality of teaching is recognized partly by the opportunity created in classes for students to engage in the best forms of study and learning.  The following are five standards developed by Fred M. Newmann and Gary G. Wehlage at the Wisconsin Center on Organization and Restructuring of Schools.  Please check each of the five scales so as to best describe teaching quality in your school.

Higher-Order Thinking

Check 1 if--in this school--teachers have students engaged exclusively in lower-order thinking operations.

Check 2 if --in this school--teachers keep students mainly in lower-order thinking operations.

Check 3 if--in this school--teachers occasionally raise questions which cause some students to engage in higher-order thinking.

Check 4 if--in this school--in most lessons, teachers engage students in at least a bit of higher-order thinking.

Check 5 if--in this school--throughout the day, teachers press all students to engage in higher-order thinking.

(21)

emphasizing lower order thinking       ..1.....2.....3.....4.....5..      emphasizing higher-order thinking

Comment?

Depth of Knowledge

Check 1 if--in this school--the teachers concentrate on superficial and fragmented knowledge.

Check 2 if--in this school--teachers mention key concepts but fail to work on deeper understandings of ideas.

Check 3 if--in this school--teachers promote deep understanding of an occasional topic but superficial understanding of many topics.

Check 4 if--in this school--teachers frequently press students to think deeply about their own knowledge bases.

Check 5 if--in this school--all teachers regularly promote the deepest understanding of subject matter.

(22)

shallow knowledge is tolerated       ..1.....2.....3.....4.....5..      deep knowledge is required

Comment?

Connectedness to the World Beyond the Classroom

Check 1 if--in this school--lesson topics and activities have no connection to experience beyond the classroom.

Check 2 if--in this school--lesson topics and activities connect only indirectly to external experience.

Check 3 if--in this school--students occasionally work on a problem or issue that people see as connected to personal experience or contemporary social issues

Check 4 if--in this school--some lesson topics and activities connect to experience beyond the classroom.

Check 4 if--in this school--students regularly work on experiential problems and contemporary social issues.

(23)

no connection with external life       ..1.....2.....3.....4.....5..      extensive connection with external life

Comment?

Substantive Conversation

Check 1 if--at this school--teachers create no opportunities for upgrading the substantive quality of conversations.

Check 2 if--at this school--teachers only rarely promote collective understanding through conversation.

Check 3 if--at this school--teachers occasionally facilitate conversations and work to get students to share understandings and build upon what had been discussed earlier.

Check 4 if--at this school--teachers get most students to share in-depth ideas in sustained, recurring conversations.

Check 5 if--at this school--teachers often get the whole class to participate in sustained conversations on key ideas.

(24)

no substantive conversation   ..1.....2.....3.....4.....5..   everyone makes substantive conversations

Comment?

Social Support for Student Achievement

Check 1 if--within these classrooms--there is sustained student derision toward academic achievement.

Check 2 if--within these classrooms--social support for achievement is evenly mixed, positive and negative.

Check 3 if--within these classrooms--teachers occasionally generate social support for high expectations, challenging work, strong effort and mutual respect for most students.

Check 4 if--within these classrooms--teachers regularly sustain high social support for student achievement.

Check 5 if--within these classrooms--none of the students are derisive toward academic achievement.

(25)

derision toward classroom achievement       ..1.....2.....3.....4.....5..      positive support for achievement

Comment?

Thank you.  Your responses will be kept confidential unless you check this box  �

which indicates you prefer to have your comments attributed to you.    .

Jean Williams, Robert Stake

PARENT RATING FORM

The Learning Communities Analysis Project				....................................................................

--an effort of the Indianapolis Public Schools			In this school, your child is in grade ____

to help each School evaluate itself.				(Or if more than one) your children are in grades _____________.

3.2

Dear Parent,

This is to add your views to other information about the quality of education provided by this school.  Together it will make up a School Evaluation Report for the year.  We will treat your response anonymously.  Any remarks you make in the margins will be given serious attention, so please feel free to comment.  For questions you feel you know nothing about, just leave it blank.

What it is that Students are Learning

It is not expected that you will know lots of the students at this school

but please answer on the basis of what you do know.

Ratings of Quality of Experience for Students at this School

It is good for young people to be a part of a good school.  On the whole,

what is the quality of day to day experience for students at this school?

____Excellent     ____Good     ____Fair     ____Poor     ____Terrible	(1)

Do you feel this school experience will be useful--helping them in the future to:

Regularly     	Sometimes high, 	Regularly

high quality 	  sometimes low   	poor quality

...direct their own learning.    .    .	_____    .    .    .    .	_____    .    .    .    .	_____	(2)

...prepare for employment.     .    .	_____    .    .    .    .	_____    .    .    .    .	_____	(3)

...participate in teamwork.      .    .	_____    .    .    .    .	_____    .    .    .    .	_____	(4)

...enjoy art and music.      .    .    .	_____    .    .    .    .	_____    .    .    .    .	_____	(5)

...solve ethical problems.       .    .	_____    .    .    .    .	_____    .    .    .    .	_____	(6)

Ratings of Individual Responsibility being Learned by These Students

| 8. Considering the students at this school, their age, and the |  | ____All but a few |
| --- | --- | --- |
| situations they face, what proportion of the students behave |  | ____Over half of them |
| in a mature and responsible fashion? |  | ____Only a few |
|  |  | ____None of them |

| 9. How much of a problem is there with students at this school acting aggressively against the school and their teachers? |  | 10. How much of a problem is there with students at this school acting aggressively against their fellow students? |
| --- | --- | --- |
| ____It is a major problem. ____It is a major problem involving only a few students. ____It is a minor problem. ____It is no problem at all. |  | ____It is a major problem. ____It is a major problem involving only a few students. ____It is a minor problem. ____It is no problem at all. |

11.  Considering their ages, how seriously do most students at this school take the responsibility of being good learners?

____Not seriously at all.      ____Most take it seriously.      ____Most take it too seriously for their own good.

| 12. How strong is the feeling of protest among students at this school when they see what is socially wrong and hurtful? |  | 13. ...and when they do protest, do they choose appropriate ways of expression? |
| --- | --- | --- |
| ____Always strong. ____Occasionally strong. ____Seldom strong. |  | ____Usually. ____Sometimes. ____Seldom. |

Ratings of the Quality of Teaching at this School

It is very important that you help us understand your views about the quality of teaching at this school.

Teaching

From all the teachers and students you have known in the last two years at this school, what is the quality of teaching of...

Regularly     	Sometimes high, 	Regularly

high quality 	 sometimes low   	poor quality

...language arts and reading.    .	_____    .    .    .  	_____    .    .    .  	_____			(14)

...math.    .    .    .    .    .    .    .	_____    .    .    .  	_____    .    .    .  	_____			(15)

...science.      .    .    .    .    .    .	_____    .    .    .  	_____    .    .    .  	_____			(16)

...social studies.  .    .    .    .    .	_____    .    .    .  	_____    .    .    .  	_____			(17)

...art and music.  .    .    .    .    .	_____    .    .    .  	_____    .    .    .  	_____			(18)

...group activities of all kinds.	_____    .    .    .  	_____    .    .    .  	_____			(19)

...work habits.    .    .    .    .    .	_____    .    .    .  	_____    .    .    .  	_____			(20)

The Teachers

| We expect teachers to do many things for our children. Please indicate how good a job the teachers do at this school. |  | These teachers do a GOOD JOB | These teachers do a POOR JOB |
| --- | --- | --- | --- |

Teachers arrange learning situations for children,

minimizing interference, recognizing when things are

right and wrong in the classroom.  .......................		______	    __	      ______	    (26)

From their own knowledge, from books, and other sources,

teachers need to make information available to their pupils.  	______	    __	      ______

Teachers need to work well with the principal, other

teachers, and the rest of the school staff.  ..............		______	    __	      ______	    (28)

Children vary greatly.  Teachers need to pay close

attention to what each individual pupil needs.  ........		______	    __       ______	    (29)

Teachers need to utilize the children's own motivation.		______	    __      ______	    (30)

Special Programs at this School

These are special programs at this school.  To the extent you are acquainted with them, how good are they?

high quality 	      average quality  	     poor quality

[Program #1]   ______________________________	_____	_____	_____		(31)

[Program #2]   ______________________________	_____	_____	_____		(32)

[Program #3]   ______________________________	_____	_____	_____		(33)

[Program #4]   ______________________________	_____	_____	_____		(34)

Ratings of the Quality of Support for this School

The remaining questions have to do with the quality of support for classroom instruction

coming from the principal's office, from the district office, from the community and the state.

School Leadership

In your view, what has been the quality of leadership

provided by the Principal of this school over the last year?

_____Excellent        _____Good        _____Fair        _____Poor        _____Terrible			(35)

The Principal cannot provide all the leadership needed.  Teachers and other staff members

need to be leaders too.  Have the teachers and staff provided their share of leadership?

_____Regular leadership        _____Only occasional leadership         _____None at all			(36)

Parental Support

37.  Teaching and learning are better if parents send their children to school with encouragement to learn.  Do parents of children at this school send the kids to school ready to learn?

_____Most do.	_____Some do, some don't.		_____Most do not.

38.  Parents support schools by paying attention to what teachers are teaching and to special schoolwide programs.  Do the parents here know what this school is doing?

_____Most do.	_____Some do, some don't.		_____Most do not.

39.  Some parents are able to volunteer help for teachers?  To the best they are able, do the parents at this school volunteer their help?

_____Most do.	_____Some do, some don't.		_____Most do not.

40  Some parents are good promoters for their school.  Others "bad mouth" their school, sometimes for good reason.  Are the parents of the children at this school good promoters?

_____Most are.	_____Some are, some are not.	_____Most are not.

IPS Strategic Plan

In 1992, the citizens of Indianapolis developed a strategic plan based on a collective vision of community responsibility for education.  Please indicate below how that plan supports the teaching and learning at this school.

| 41. Did the IPS Strategic Plan accurately identify crucial educational problems facing the community's schools? | _____Yes, it did. | ___No, it did not. | ___I have no knowledge about it. |
| --- | --- | --- | --- |
| 42. Is the IPS Strategic Plan a valuable guideline for school improvement at this school? | _____Yes, it is. | ____No, it is not. | ___I have no knowledge about it. |
| 43. At this school, is it difficult to get outside support even for problems identified in the Strategic Plan? | _____Yes, it is. | ____No, it is not. | ___I have no knowledge about it. |

School System Support

This school depends on the school district, the community, and the state for financial support, direction, and encouragement.  How good a job are they doing?

Does Good Job      Does Poor Job

Does the Indianapolis Public School District

support this school the way it should?		______           __          ______	(44)

Does the City of Indianapolis

support this school the way it should?		      ______           __          ______	(45)

Does the State of Indiana

support this school the way it should?		      ______           __          ______	(46)

Thank you.  Your responses will be kept confidential unless you check here ____

which indicates you prefer to have your comments attributed to you.

Jean Williams, Robert Stake   (317) 244-8160

# Program Specialist Rating Form

This is to add your views to other information about the quality of education provided by this school.  Together it will make up a School Evaluation Report for the year.  We will treat your response anonymously.  Any remarks you make in the margins will be given serious attention.

Ratings of the Quality of Teaching at this School

It is very important that you help us understand your views about the quality of teaching at this school.  Since it may be different for different subjects being taught, please answer each of the following as best you can.

Frameworks Teaching

From all the teachers and students you have known in the last two years at this school, what is the quality of teaching of:

Regularly     	     Sometimes high, 	       Regularly

high quality 	      sometimes low   	      poor quality

language arts, reading, math	_____	_____	_____

science and social studies	_____	_____	_____

art, music, aesthetics	_____	_____	_____

group activities of all kinds	_____	_____	_____

economics and working	_____	_____	_____

Teacher Roles

We expect teachers to do many things for our children.

For each of the five roles below,  please indicate

how good a job the teachers do at this school.

Do Good Job      Do Poor Job

Teachers need to arrange learning situations for children,

minimizing interference, recognizing when things are

right and wrong in the classroom.  .......................	______		______

Teachers need to make information available to

their pupils, from their own knowledge, from

books, and other sources.  ................................	______		______

Teachers need to work well with the principal, other

teachers, and the rest of the school staff.  ..............	______		______

Children are different.  Teachers need to pay close

attention to what each individual pupil needs.  ........	______		______

Some things children need to learn are not very interesting.

Teachers need to find ways to motivate children.  ......	______		______

Special Programs at this School

These are the special programs at this school.  To the extent you are acquainted with them, how good are they

Regularly     	     Sometimes high, 	       Regularly

high quality 	      sometimes low   	      poor quality

Special Program #1	_____	_____	_____

Special Program #2	_____	_____	_____

Special Program #3	_____	_____	_____

Special Program #4	_____	_____	_____

School Leadership

In your view, what has been the quality of leadership

provided by the Principal of this school for the last year?

_____Excellent        _____Good        _____Fair        _____Poor        _____Terrible

The Principal cannot provide all the leadership needed.

Teachers and other members of the staff need to be leaders too.

Have the teachers and staff provided their share of leadership?

_____Regular leadership        Only occasional leadership         _____None at all

# Opportunity Standards

(Insert the Wisconsin scales here from the Teachers Rating Form)